## Overview
LEARN ROS 2 IN 30 DAYS - OVERVIEW
1. THE HONEST DURATION ANSWER
Can you learn ROS 2 in 30 days? | YES for a working foundation: CLI, nodes/topics/services/actions, launch, URDF, TF2, Gazebo simulation, ros2_control, SLAM + Nav2 basics, and micro-ROS on a microcontroller. At ~3 hrs/day this plan is ~99 hours.
Is 30 days enough to master it? | NO. Job-ready / production-level skill (real hardware, tuning Nav2, perception, MoveIt, C++ depth) typically takes 3-6 months of regular practice. See the After_30_Days sheet for weeks 5-12.
Prerequisites | Basic Linux terminal, Python (and C/C++ basics - you already have embedded C), Git. If Linux is new, add 2-3 extra days before Day 1.
2. PACE CALCULATOR (edit the blue cell)
Total plan hours | 99
Your study hours per day | 3 | <- change me
Days needed at your pace | 33
Rule of thumb | 1 hr/day = ~99 days ¦ 2 hrs/day = ~50 days ¦ 3 hrs/day = ~33 days ¦ 4 hrs/day = ~25 days
3. PROGRESS TRACKER (auto-updates from the Plan sheet)
Days completed | 0
Days in progress | 0
Hours completed | 0
% complete (by hours) | 0%
4. WEEKLY ROADMAP (color key used in the plan)
Week 1 (Days 1-7) | Install, CLI tools, workspace, first Python pub/sub
Week 2 (Days 8-14) | C++, services, custom interfaces, params, launch, actions, QoS
Week 3 (Days 15-21) | TF2, URDF/Xacro, Gazebo Harmonic, sensors, simulated robot
Week 4 (Days 22-28) | ros2_control, SLAM, Nav2, micro-ROS on MCU
Days 29-30 | Capstone project, documentation, demo
5. TOOLS & VERSIONS USED
ROS distribution | ROS 2 Jazzy Jalisco (LTS, supports Ubuntu 24.04). Newer releases exist, but Jazzy is still supported and has the widest tutorial coverage + Gazebo Harmonic pairing.
Language order | Python (rclpy) first for speed, then C++ (rclcpp) from Day 8.
Simulator | Gazebo Harmonic via ros_gz (the supported pairing for Jazzy).
Note on videos | Some popular video series (Robocademy = Humble; older Articulated Robotics = Foxy/Humble) use older distros. Concepts are identical; only a few commands/package names differ - always cross-check with the Jazzy docs.
Assumption | Hours per day in the plan are my estimates for a motivated learner with some programming background - not measured data. Adjust the blue cells.

## Plan_30_Days
ROS 2 (Jazzy) - 30-DAY DAY-BY-DAY PLAN
Hours are my estimates for a focused learner (blue = editable). Docs links = official/verified pages. Video column = playlist/channel + the exact topic to search inside it. Update Status (dropdown) as you go.
Day | Week / Phase | Topic | What to do (tasks) | Hours | Docs / reading link | Video lecture link | Search inside video source | Deliverable (proof you learned it) | Status | Date done
1 | WEEK 1 - Foundations | Install Ubuntu 24.04 + ROS 2 Jazzy | Set up Ubuntu 24.04 (dual-boot, VM or WSL2 is OK but native is best). Install ros-jazzy-desktop. Add 'source /opt/ros/jazzy/setup.bash' to ~/.bashrc. Run the talker/listener demo. | 3 | https://docs.ros.org/en/jazzy/Installation.html | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | Robocademy: ROS 2 installation / Linux basics session | talker + listener demo running | Not started
2 | WEEK 1 - Foundations | CLI tools: turtlesim, nodes, rqt | Run turtlesim, drive it with teleop. Use ros2 node list/info, rqt, rqt_graph. Understand what a node is. | 3 | https://docs.ros.org/en/jazzy/Tutorials.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 Tutorials playlist: nodes / turtlesim | Screenshot of rqt_graph with turtlesim | Not started
3 | WEEK 1 - Foundations | Topics & Services (CLI) | ros2 topic list/echo/pub/hz/info, ros2 interface show, ros2 service list/call. Understand pub/sub vs request/response. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Services/Understanding-ROS2-Services.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 Tutorials playlist: topics / services | Publish a Twist to move turtle from the terminal | Not started
4 | WEEK 1 - Foundations | Parameters, Actions, rqt_console, Launch, rosbag | ros2 param get/set/dump, ros2 action send_goal, rqt_console, first launch file, ros2 bag record/play. | 3 | https://docs.ros.org/en/jazzy/Tutorials.html | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | Robocademy: ROS 2 beginner CLI sessions | Record and replay a rosbag of turtlesim | Not started
5 | WEEK 1 - Foundations | Workspace, colcon, packages | Create ~/ros2_ws, create a Python package (ament_python), build with colcon build, source install/setup.bash. Learn package.xml, setup.py. | 3 | https://docs.ros.org/en/jazzy/Tutorials.html | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: ROS workspace / packages | Your own package builds and runs | Not started
6 | WEEK 1 - Foundations | First publisher & subscriber (Python / rclpy) | Write a minimal publisher and subscriber in Python. Understand spin, callbacks, timers, logging. | 3 | https://docs.ros.org/en/jazzy/Tutorials.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 Tutorials playlist: publisher subscriber python | Two nodes talking over /chatter | Not started
7 | WEEK 1 - Foundations | Week 1 review + mini project | Write a node that publishes velocity commands to draw a square with turtlesim; write another node that subscribes to /turtle1/pose and logs it. | 4 | https://docs.ros.org/en/jazzy/Tutorials.html | https://www.youtube.com/@ArticulatedRobotics/videos | Review videos of days 1-6 at 1.5x | Turtlesim square-drawing node (push to GitHub) | Not started
8 | WEEK 2 - Core Programming | Publisher & subscriber in C++ (rclcpp) | Repeat day 6 in C++ using ament_cmake. Compare Python vs C++ structure. (Your embedded C/C++ background will help here.) | 3 | https://docs.ros.org/en/jazzy/Tutorials/Writing-A-Simple-Cpp-Publisher-And-Subscriber.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 C++ publisher subscriber | C++ pub/sub package builds | Not started
9 | WEEK 2 - Core Programming | Services: server & client | Write a service server and client (Python first, then C++). Use AddTwoInts style service; call from CLI and from code. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Writing-A-Simple-Cpp-Service-And-Client.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 service server client tutorial | Working service in both languages | Not started
10 | WEEK 2 - Core Programming | Custom messages & services | Create a separate interfaces package (my_interfaces). Define custom .msg and .srv. Use them in your nodes. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | https://www.youtube.com/@ArticulatedRobotics/videos | ROS 2 custom interfaces msg srv | my_interfaces package with 1 msg + 1 srv | Not started
11 | WEEK 2 - Core Programming | Parameters + Launch files | Declare/use parameters in a class. Write Python launch files that start multiple nodes with YAML parameters and remapping. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | Robocademy: launch files & parameters | Launch file starting 3 nodes with a YAML config | Not started
12 | WEEK 2 - Core Programming | Actions: server & client | Write an action server/client (e.g., Countdown or Fibonacci) with feedback and cancel. Learn when to use topic vs service vs action. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | ROS 2 actions server client python | Action with feedback working | Not started
13 | WEEK 2 - Core Programming | QoS, executors, logging, ros2doctor | Learn QoS profiles (reliable/best-effort, durability), callback groups & executors, log levels, ros2 doctor. | 3 | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | https://roboticsbackend.com | Robotics Back-End: ROS 2 QoS / executors | QoS-mismatch demo and fix | Not started
14 | WEEK 2 - Core Programming | Week 2 mini project: sensor monitor system | Build: simulated sensor node (params: rate, noise) -> monitor node (alarm service + threshold param) -> launch file. Think of it as your own telemetry pipeline. | 4 | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | https://www.youtube.com/@ArticulatedRobotics/videos | Review week 2 topics | Sensor + monitor package with launch file | Not started
15 | WEEK 3 - Modeling & Simulation | TF2: coordinate frames | Understand frames, static & dynamic transforms, tf2_ros, view_frames, RViz2 TF display. Write a broadcaster and a listener. | 3 | https://docs.ros.org/en/jazzy/Tutorials.html | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | ROS2 Tutorials playlist: TF2 / RViz | TF tree with 3+ frames in RViz2 | Not started
16 | WEEK 3 - Modeling & Simulation | URDF basics | Describe a robot: links, joints, visual/collision/inertial. Build a simple differential-drive chassis in URDF. | 3 | https://articulatedrobotics.xyz/mobile-robot-1-project-overview/ | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: URDF robot model | chassis.urdf viewable in RViz2 | Not started
17 | WEEK 3 - Modeling & Simulation | Xacro, robot_state_publisher, RViz2 | Convert URDF to Xacro (macros, properties). Use robot_state_publisher + joint_state_publisher_gui. Configure RViz2. | 3 | https://articulatedrobotics.xyz/category/build-a-mobile-robot-with-ros | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: Xacro / robot_state_publisher | Parametrised Xacro robot with moving wheels | Not started
18 | WEEK 3 - Modeling & Simulation | Gazebo (Harmonic) + ros_gz bridge | Install Gazebo Harmonic + ros_gz (Jazzy pairing). Run an example world, learn gz topics, bridge a topic with ros_gz_bridge. | 3 | https://gazebosim.org/docs/latest/ros_installation | https://github.com/gazebosim/ros_gz | Gazebo Harmonic ROS 2 integration tutorial | Gazebo world running, topic bridged to ROS | Not started
19 | WEEK 3 - Modeling & Simulation | Spawn your robot in Gazebo + diff-drive | Spawn your Xacro robot in Gazebo, add the diff-drive system plugin, drive with teleop_twist_keyboard. | 4 | https://ros2-tutorial.readthedocs.io/en/latest/gazebo/ros_gz_bridge.html | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: Simulating robot in Gazebo | Robot driven by keyboard in Gazebo | Not started
20 | WEEK 3 - Modeling & Simulation | Simulated sensors: LiDAR, camera, IMU | Add LiDAR + camera + IMU to the robot, bridge topics, view in RViz2 (LaserScan, Image). | 3 | https://ros2-tutorial.readthedocs.io/en/latest/gazebo/ros_gz_bridge.html | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: LIDAR / camera in simulation | LaserScan + camera image visible in RViz2 | Not started
21 | WEEK 3 - Modeling & Simulation | Week 3 mini project: simulated mobile robot | Single launch file: Gazebo + robot + bridges + RViz2 + teleop. Clean up package structure; push to GitHub with README. | 4 | https://articulatedrobotics.xyz/category/build-a-mobile-robot-with-ros | https://www.youtube.com/@ArticulatedRobotics/videos | Review week 3 topics | One-command simulation launch (GitHub) | Not started
22 | WEEK 4 - Control, Nav & Hardware | ros2_control concepts | Study controller manager, hardware interface, controllers (diff_drive_controller, joint_state_broadcaster). Read the docs end-to-end. | 3 | https://control.ros.org/jazzy/index.html | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: ros2_control | Diagram of ros2_control for your robot | Not started
23 | WEEK 4 - Control, Nav & Hardware | ros2_control with Gazebo | Replace the diff-drive plugin with gz_ros2_control + diff_drive_controller. Load controllers from YAML. | 4 | https://control.ros.org/jazzy/index.html | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: ros2_control simulation | Robot driven through ros2_control | Not started
24 | WEEK 4 - Control, Nav & Hardware | SLAM: build a map | Run slam_toolbox in simulation, drive around, save the map with map_saver. | 3 | https://automaticaddison.com/tutorials/ | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: SLAM Toolbox / mapping | Saved map.pgm + map.yaml of your world | Not started
25 | WEEK 4 - Control, Nav & Hardware | Nav2 introduction | Read Nav2 concepts (planner, controller, costmaps, behavior trees). Run the Nav2 quickstart with TurtleBot3 simulation. | 3 | https://docs.nav2.org/jazzy/getting_started/ | https://roboticsbackend.com | Robotics Back-End: ROS 2 Nav2 navigation stack | TurtleBot3 navigating to a goal in Nav2 | Not started
26 | WEEK 4 - Control, Nav & Hardware | Nav2 on your own robot | Configure nav2_params.yaml for your robot + saved map, localise with AMCL, send goals from RViz2 and from a Python node. | 4 | https://docs.nav2.org/jazzy/getting_started/ | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics: Nav2 autonomous navigation | Your robot navigates autonomously in sim | Not started
27 | WEEK 4 - Control, Nav & Hardware | micro-ROS: first application | Follow the micro-ROS tutorials: first app on Linux, then on an MCU (ESP32 / STM32 / Teensy). Learn rcl/rclc API and the micro-ROS Agent. | 3 | https://micro.ros.org/docs/tutorials/core/overview | https://micro.ros.org/docs/tutorials/core/overview | micro-ROS first application ESP32 / STM32 | MCU node visible in 'ros2 node list' | Not started
28 | WEEK 4 - Control, Nav & Hardware | micro-ROS: sensor / actuator from MCU | Publish a real sensor value (IMU, ultrasonic, temperature) from the MCU and subscribe to a command topic to drive an LED or motor driver. | 4 | https://micro.ros.org/docs/tutorials/core/overview | https://roboticsbackend.com | micro-ROS publisher subscriber ESP32 | Hardware sensor data plotted in rqt / RViz2 | Not started
29 | CAPSTONE | Capstone build (choose one) | Option A: Autonomous nav robot in sim with custom world, map and Python 'patrol' node using Nav2 action. Option B: MCU sensor -> micro-ROS -> ROS 2 dashboard (rqt_plot/Foxglove) + custom services. | 4 | https://automaticaddison.com/tutorials/ | https://www.youtube.com/@ArticulatedRobotics/videos | Articulated Robotics + Nav2 docs | Capstone running end-to-end | Not started
30 | CAPSTONE | Finish, document, demo, self-review | Write README with architecture diagram, record a 2-minute demo video, push to GitHub, post on ROS Discourse. List weak areas and plan the next 8 weeks (see After_30_Days sheet). | 4 | https://discourse.openrobotics.org | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | Revisit weakest topic videos | GitHub repo + demo video + gap list | Not started
|  |  | TOTAL HOURS | 99

## Resources
BEST RESOURCES (all free)
Resource | Type | Best for | Link | Priority
ROS 2 Jazzy official tutorials | Official docs | The core path: CLI tools, client libraries, intermediate topics. Do these in order. | https://docs.ros.org/en/jazzy/Tutorials.html | MUST
ROS 2 Jazzy install guide | Official docs | Day 1 installation on Ubuntu 24.04. | https://docs.ros.org/en/jazzy/Installation.html | MUST
Articulated Robotics - Build a mobile robot with ROS | Blog + video series | Best URDF -> Gazebo -> ros2_control -> SLAM -> Nav2 storyline. | https://articulatedrobotics.xyz/category/build-a-mobile-robot-with-ros | MUST
Articulated Robotics YouTube channel | YouTube channel | Video lectures for the series above. | https://www.youtube.com/@ArticulatedRobotics/videos | MUST
ROS2 Tutorials playlist (RViz, TF2, services) | YouTube playlist | Short videos on RViz2, TF2 coordinate frames, service server/client. | https://www.youtube.com/playlist?list=PL8MgID9MCju0GMQDTWzYmfiU3wY_Zdjl5 | HIGH
Robocademy ROS developer learning path | 120+ free live sessions | Deep, long-form lectures with slides + GitHub notes (Humble-based). | https://robocademy.com/blog/open-sourcing-ros-developer-learning-path-2-0-by-robocademy | HIGH
ros_gz (ROS <-> Gazebo) | GitHub repo | Version pairing table: Jazzy <-> Gazebo Harmonic. | https://github.com/gazebosim/ros_gz | HIGH
Gazebo - ROS installation page | Official docs | Installing Gazebo for your ROS distro. | https://gazebosim.org/docs/latest/ros_installation | HIGH
ros_gz_bridge guide | Community tutorial | Mapping Gazebo topics to ROS 2 topics. | https://ros2-tutorial.readthedocs.io/en/latest/gazebo/ros_gz_bridge.html | HIGH
ros2_control (Jazzy) | Official docs | Controllers, hardware interfaces, gz_ros2_control. | https://control.ros.org/jazzy/index.html | HIGH
Nav2 getting started (Jazzy) | Official docs | Nav2 quickstart + concepts. | https://docs.nav2.org/jazzy/getting_started/ | HIGH
micro-ROS tutorials | Official docs | ROS 2 on ESP32 / STM32 / Teensy - very relevant for embedded work. | https://micro.ros.org/docs/tutorials/core/overview | HIGH
Automatic Addison | Blog tutorials | Step-by-step ROS 2 projects (SLAM, sensor fusion, Nav2). | https://automaticaddison.com/tutorials/ | MEDIUM
The Robotics Back-End | Blog + YouTube | ROS 2 guides, Nav2, learning-path articles. | https://roboticsbackend.com | MEDIUM
ROS Discourse | Community forum | Ask questions, see announcements, share your capstone. | https://discourse.openrobotics.org | MEDIUM

## After_30_Days
WEEKS 5-12: FROM FOUNDATION TO JOB-READY (suggested)
Weeks | Focus | What to learn / build | Link | Hours / week
Week 5-6 | Intermediate ROS 2 + C++ depth | Composable nodes, lifecycle nodes, executors/callback groups, rosbag2 workflows, testing (launch_testing, gtest/pytest), Docker for ROS 2. | https://docs.ros.org/en/jazzy/Tutorials/Intermediate.html | 6
Week 7-8 | Real hardware | Run ROS 2 Jazzy on a Raspberry Pi 5 / Jetson, ros2_control with a real hardware interface (motors + encoders via your MCU), real IMU/LiDAR drivers. | https://articulatedrobotics.xyz/mobile-robot-13-ros2-control-real/ | 8
Week 9-10 | Navigation tuning + SLAM | Tune Nav2 costmaps/controllers, behavior trees, sensor fusion (robot_localization), multi-map / waypoint following. | https://docs.nav2.org/jazzy/getting_started/ | 8
Week 11 | Perception | OpenCV with cv_bridge, depth camera, point clouds, AprilTag/ArUco detection integrated with Nav2. | https://automaticaddison.com/tutorials/ | 8
Week 12 | Portfolio / specialization | Pick one: MoveIt 2 (arms), micro-ROS production firmware, or your own robot product. Publish a polished GitHub repo + demo video. | https://discourse.openrobotics.org | 10
|  |  | Total hours (weeks 5-12, assumption-based) | 40
Note: week-wise hours are my rough estimates (blue = editable). Total = 30-day plan + weeks 5-12 is roughly a 3-month path.